## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Backend Team | 2025-09-17 | Incorrect data type for 'departure_time' | Sprint 1 | Backend Team | Standards | Changed column data type to TIMESTAMP | 2025-09-18 | Closed | Changed column to TIMESTAMP
2 | Backend Team | 2025-09-25 | Search API returns 500 Error (destination not found) | Sprint 2 | Backend Team | Logical | Added try-except block for missing destinations | 2025-09-25 | Closed | Need to add try-except block.
3 | Backend Team | 2025-09-30 | Dynamic price lower than base price (at 99% full) | Sprint 2 | Backend Team | Logical | Reviewed and corrected pricing formula | 2025-10-01 | Closed | Pricing logic error.
4 | Backend Team | 2025-10-02 | Demand simulation script crashes after 1 hour | Sprint 2 | Backend Team | Maintainability | Implemented database connection pooling | 2025-10-02 | Closed | Need to implement connection pooling.
5 | Backend Team | 2025-10-12 | Race condition allows double booking of last seat | Sprint 3 | Backend Team | Logical | Planned to add database transaction locks | 2025-10-12 | Closed | Needs DB transaction lock.
6 | Backend Team | 2025-10-16 | Cancellation API fails for mixed case PNRs | Sprint 3 | Backend Team | Standards | Modify query to handle case-insensitive PNR comparison | 2025-10-16 | Closed | Query should be case-insensitive.
7 | Frontend Team | 2025-10-24 | Dynamic Price not displayed on search results | Sprint 4 | Backend Team | User Interface | Corrected JSON key mapping in frontend | 2025-10-24 | Closed | Mapped the wrong JSON key.
8 | Frontend Team | 2025-10-25 | Book Now' button active when no flight is selected | Sprint 4 | Backend Team | User Interface | Updated button state logic based on selection | 2025-10-25 | Closed | Button state not tied to selection.
9 | Frontend Team | 2025-10-26 | Date in search results is formatted as YYYY-MM-DD | Sprint 4 | Backend Team | User Interface | Applied date formatting function (DD/MM/YYYY) | 2025-10-27 | Closed | Applied date formatting function.
10 | Frontend Team | 2025-10-29 | Downloaded JSON receipt is missing the PNR | Sprint 4 | Backend Team | User Interface | Passed PNR to receipt component | 2025-10-29 | Closed | Forgot to pass PNR to receipt component

## Sheet2
Logical
User Interface
Maintainability
Standards
Others